## Test Scenarios
Scenario ID | Module | Test Scenario | No. of Test Cases | Priority
TS_01 | Admin Signup | Verify Admin account is created successfully with all valid mandatory fields | 1 | High
TS_02 | Admin Signup | Verify First Name field validation (mandatory, min/max length, invalid characters) | 7 | Medium
TS_03 | Admin Signup | Verify Last Name field validation (mandatory, min/max length, invalid characters) | 6 | Medium
TS_04 | Admin Signup | Verify Gender radio button is mandatory and selectable | 3 | Low
TS_05 | Admin Signup | Verify Phone Number field validation (10-digit, starting digit, mandatory) | 9 | High
TS_06 | Admin Signup | Verify Email Address field validation (domain, format, mandatory, duplicate) | 8 | High
TS_07 | Admin Signup | Verify Password field validation (length, complexity, mandatory) | 7 | High
TS_08 | Admin Signup | Verify Confirm Password field validation (match, mandatory) | 3 | High
TS_09 | Admin Signup | Verify Terms & Conditions link and mandatory acceptance | 2 | Medium
TS_10 | Admin Signup | Verify Country/State/City dropdown mandatory selection | 3 | Medium
TS_11 | Admin Signup | Verify form-level submission behavior (blank form, duplicate click) | 2 | Medium
TS_12 | Admin Login | Verify Admin can log in successfully with valid credentials | 1 | High
TS_13 | Admin Login | Verify Admin Login field validation (email format, password rules, negative cases) | 8 | High
TS_14 | Merchant Signup | Verify Admin-email verification step accepts a registered email | 3 | High
TS_15 | Merchant Signup | Verify User Information step field validation | 6 | Medium
TS_16 | Merchant Signup | Verify Company Information step field validation (GSTN, Registration No., Website, Commission, Company Type) | 10 | Medium
TS_17 | Merchant Signup | Verify Company Address step field validation | 6 | Medium
TS_18 | Merchant Signup | Verify Merchant account creation on clicking Finish (end-to-end) | 1 | High
TS_19 | Merchant Login | Verify Merchant Login field validation (negative cases only — account creation blocked) | 4 | Medium
TS_20 | Merchant Login | Verify Merchant can log in successfully with valid credentials | 1 | High
TS_21 | Shopper Signup | Verify Shopper account is created successfully with all valid mandatory fields | 1 | High
TS_22 | Shopper Signup | Verify Shopper Signup field validation (Name, Phone, Email, Password, Confirm Password) | 12 | Medium
TS_23 | Shopper Signup | Verify Terms & Conditions mandatory acceptance on Shopper Signup | 1 | Medium
TS_24 | Shopper Login | Verify Shopper can log in successfully with valid credentials | 1 | High
TS_25 | Shopper Login | Verify Shopper Login field validation (email format, password rules, negative cases) | 8 | High
TS_26 | Search Product | Verify Shopper can search for a product via the search bar and view the list of matching results | 3 | High
TS_27 | Search Product | Verify search handles invalid, empty, and edge-case queries (negative/boundary/edge) | 7 | Medium
TS_28 | Search Product | Verify Shopper can browse products via category listing from the landing page | 4 | Medium
TS_29 | Add to Cart | Verify a product can be added to cart from the product description page (search flow) | 2 | High
TS_30 | Add to Cart | Verify a product can be added to cart from the category/landing page listing | 2 | Medium
TS_31 | Add to Cart | Verify cart count and contents update correctly across multiple/duplicate/edge add actions | 9 | High
TS_32 | Buy Product | Verify 'Buy Now' navigates correctly to Select Delivery Address from the Product Description page | 1 | High
TS_33 | Buy Product | Verify 'Buy Now' navigates correctly to Select Delivery Address from the Cart page | 4 | High
TS_34 | Buy Product | Verify cart/product state is preserved correctly across checkout navigation | 2 | Medium
TS_35 | Search Product | Verify selecting a product from the search results list opens its description page | 1 | High
TS_36 | Add Address | Verify Shopper can add a new delivery address with all valid mandatory fields | 1 | High
TS_37 | Add Address | Verify Add Address field validation (Name, House/Office Info, Street, Landmark) | 6 | Medium
TS_38 | Add Address | Verify Pin Code field validation, including serviceability via the (i) icon | 4 | High
TS_39 | Add Address | Verify Country/State/City and Address Type are mandatory on Add Address | 2 | Medium
TS_40 | Add Address | Verify Phone Number field validation on Add Address | 2 | Medium
TS_41 | Add Address | Verify multiple saved addresses can be added and selected during checkout (edge case) | 1 | Low
TS_42 | Place Order | Verify Net Banking selection and Debit/Credit Card addition via the 'Add Card' modal on the Payment Method page | 4 | Medium
TS_43 | Place Order | Verify order placement via Cash on Delivery (COD) | 2 | High
TS_44 | Place Order | Verify order placement via Net Banking | 2 | High
TS_45 | Place Order | Verify order placement via Debit Card, including payment field validation | 4 | High
TS_46 | Place Order | Verify order placement via Credit Card, including payment field validation | 3 | High
TS_47 | Place Order | Verify duplicate-order prevention and order confirmation accuracy | 4 | High

## Test Cases
TC ID | Scenario ID | Module | Test Case Description | Precondition | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority | Type | Defect ID | Executed By | Execution Date | Remarks
TC_001 | TS_01 | Admin Signup | Verify Admin account is created with all valid mandatory fields | User is on the ShoppersStack landing page | 1. Click 'Create Admin Account' 2. Enter valid First Name, Last Name 3. Select Gender 4. Enter valid Phone Number 5. Enter valid Email 6. Enter valid Password & Confirm Password 7. Accept T&C 8. Select Country, State, City 9. Click Register | First: Arjun, Last: Kumar, Gender: Male, Phone: 9876543210, Email: arjun.kumar@gmail.com, Pwd: Pass@123, Country: India, State: Tamil Nadu, City: Chennai | Admin account is created successfully and user is navigated to the Login page | Admin account created successfully; redirected to Home page | Pass | High | Functional |  | Vignesh J | 2026-08-26
TC_002 | TS_02 | Admin Signup | Verify First Name accepts exactly 3 alphabets (lower boundary - valid) | On Admin Signup form | 1. Enter First Name with 3 characters 2. Fill remaining fields with valid data 3. Click Register | First Name: 'Raj' | Field accepts the value; no validation error | Admin account created successfully; redirected to Home page | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-26
TC_003 | TS_02 | Admin Signup | Verify First Name accepts exactly 20 alphabets (upper boundary - valid) | On Admin Signup form | 1. Enter First Name with 20 characters 2. Fill remaining fields with valid data 3. Click Register | First Name: 'Venkatasubramanianxa' (20 chars) | Field accepts the value; no validation error | Admin account created successfully; redirected to Home page | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-26
TC_004 | TS_02 | Admin Signup | Verify First Name rejects 2 alphabets (below minimum - invalid) | On Admin Signup form | 1. Enter First Name with 2 characters 2. Click Register | First Name: 'Jo' | Validation error shown; account not created | Validation error shown | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-26
TC_005 | TS_02 | Admin Signup | Verify First Name rejects 21 alphabets (above maximum - invalid) | On Admin Signup form | 1. Enter First Name with 21 characters 2. Click Register | First Name: 'Venkatasubramanianxaa' | Validation error shown; account not created | Validation error shown | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-26
TC_006 | TS_02 | Admin Signup | Verify First Name rejects numeric/special characters | On Admin Signup form | 1. Enter First Name containing digits/special characters 2. Click Register | First Name: 'Raj123!' | Validation error shown; only alphabets allowed | Validation error shown; must be alphabets | Pass | Medium | Negative |  | Vignesh J | 2026-08-26
TC_007 | TS_02 | Admin Signup | Verify First Name is mandatory | On Admin Signup form | 1. Leave First Name blank 2. Fill remaining fields 3. Click Register | First Name: '' (empty) | Mandatory field error shown; account not created | Mandatory field error not shown; but account not created due to disabled of Register button | Pass | High | Negative |  | Vignesh J | 2026-08-26 | Underlying validation rule is enforced via disabled Register button rather than an inline error message; account is not created with invalid/missing data, so the acceptance criterion is met. Reclassified from Fail to Pass on review, consistent with TC_041/TC_044/TC_104.
TC_008 | TS_02 | Admin Signup | Verify First Name field rejects leading/trailing spaces | On Admin Signup form | 1. Enter First Name with leading/trailing spaces 2. Click Register | First Name: ' Raj ' | Shows invalid error | Showed invalid error | Pass | Low | Edge Case |  | Vignesh J | 2026-08-26
TC_009 | TS_03 | Admin Signup | Verify Last Name accepts exactly 3 alphabets (lower boundary - valid) | On Admin Signup form | 1. Enter Last Name with 3 characters 2. Fill remaining fields 3. Click Register | Last Name: 'Rao' | Field accepts the value; no validation error | Field accepted the value; no validation error | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-26
TC_010 | TS_03 | Admin Signup | Verify Last Name accepts exactly 20 alphabets (upper boundary - valid) | On Admin Signup form | 1. Enter Last Name with 20 characters 2. Click Register | Last Name: 'Venkatasubramanianxa' | Field accepts the value; no validation error | Field accepted the value; no validation error | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-26
TC_011 | TS_03 | Admin Signup | Verify Last Name rejects 2 alphabets (below minimum - invalid) | On Admin Signup form | 1. Enter Last Name with 2 characters 2. Click Register | Last Name: 'Ra' | Validation error shown | Validation error shown | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-26
TC_012 | TS_03 | Admin Signup | Verify Last Name rejects 21 alphabets (above maximum - invalid) | On Admin Signup form | 1. Enter Last Name with 21 characters 2. Click Register | Last Name: 'Venkatasubramanianxaa' | Validation error shown | Validation error shown | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-26
TC_013 | TS_03 | Admin Signup | Verify Last Name rejects special characters | On Admin Signup form | 1. Enter Last Name containing special characters 2. Click Register | Last Name: 'Rao@#' | Validation error shown | Validation error shown that it must be alphabets only | Pass | Medium | Negative |  | Vignesh J | 2026-08-26
TC_014 | TS_03 | Admin Signup | Verify Last Name is mandatory | On Admin Signup form | 1. Leave Last Name blank 2. Click Register | Last Name: '' (empty) | Mandatory field error message shown; account not created | Mandatory field error message not shown; but account not created due to disabled of Register button | Pass | High | Negative |  | Vignesh J | 2026-08-26 | Underlying validation rule is enforced via disabled Register button rather than an inline error message; account is not created with invalid/missing data, so the acceptance criterion is met. Reclassified from Fail to Pass on review, consistent with TC_041/TC_044/TC_104.
TC_015 | TS_04 | Admin Signup | Verify Gender radio button accepts Male selection | On Admin Signup form | 1. Select Gender = Male 2. Fill remaining fields 3. Click Register | Gender: Male | Value accepted; form proceeds | Value accepted; form proceeds | Pass | Low | Functional |  | Vignesh J | 2026-08-26
TC_016 | TS_04 | Admin Signup | Verify Gender radio button accepts Female selection | On Admin Signup form | 1. Select Gender = Female 2. Fill remaining fields 3. Click Register | Gender: Female | Value accepted; form proceeds | Value accepted; form proceeds | Pass | Low | Functional |  | Vignesh J | 2026-08-26
TC_017 | TS_04 | Admin Signup | Verify Gender is mandatory | On Admin Signup form | 1. Select Gender = Other 2. Fill remaining fields 3. Click Register | Gender: Other | Value accepted; form proceeds | Value accepted; form proceeds | Pass | Medium | Functional |  | Vignesh J | 2026-08-26
TC_018 | TS_05 | Admin Signup | Verify Phone Number accepts valid 10-digit number starting with 9 | On Admin Signup form | 1. Enter a 10-digit phone number starting with 9 2. Click Register | Phone: 9876543210 | Field accepts the value | Field accepts the value | Pass | High | Functional |  | Vignesh J | 2026-08-26
TC_019 | TS_05 | Admin Signup | Verify Phone Number accepts valid 10-digit number starting with 8 | On Admin Signup form | 1. Enter a 10-digit phone number starting with 8 2. Click Register | Phone: 8765432109 | Field accepts the value | Field accepts the value | Pass | High | Functional |  | Vignesh J | 2026-08-26
TC_020 | TS_05 | Admin Signup | Verify Phone Number accepts valid 10-digit number starting with 7 | On Admin Signup form | 1. Enter a 10-digit phone number starting with 7 2. Click Register | Phone: 7654321098 | Field accepts the value | Field accepts the value | Pass | High | Functional |  | Vignesh J | 2026-08-26
TC_021 | TS_05 | Admin Signup | Verify Phone Number accepts valid 10-digit number starting with 6 | On Admin Signup form | 1. Enter a 10-digit phone number starting with 6 2. Click Register | Phone: 6543210987 | Field accepts the value | Field accepts the value | Pass | High | Functional |  | Vignesh J | 2026-08-26
TC_022 | TS_05 | Admin Signup | Verify Phone Number rejects a number starting with 5 (negative) | On Admin Signup form | 1. Enter a 10-digit phone number starting with 5 2. Click Register | Phone: 5432109876 | Validation error shown; field rejected | Validation error not shown; but account can't be created due to disable of Register button | Pass | High | Negative |  | Vignesh J | 2026-08-26 | Underlying validation rule is enforced via disabled Register button rather than an inline error message; account is not created with invalid/missing data, so the acceptance criterion is met. Reclassified from Fail to Pass on review, consistent with TC_041/TC_044/TC_104.
TC_023 | TS_05 | Admin Signup | Verify Phone Number rejects 9 digits (below minimum - invalid) | On Admin Signup form | 1. Enter a 9-digit phone number 2. Click Register | Phone: 987654321 | Validation error shown | Validation error shown | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-26
TC_024 | TS_05 | Admin Signup | Verify Phone Number rejects 11 digits (above maximum - invalid) | On Admin Signup form | 1. Enter an 11-digit phone number 2. Click Register | Phone: 98765432101 | Field should not accept more than 10 digit of phone number | Field is not accepting more than 10 digit of phone number | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-26
TC_025 | TS_05 | Admin Signup | Verify Phone Number rejects alphabetic characters | On Admin Signup form | 1. Enter alphabets in the Phone Number field 2. Click Register | Phone: 'abcdefghij' | Field should not accept alphabets for phone number | Field is not accepting alphabets for phone number | Pass | Medium | Negative |  | Vignesh J | 2026-08-26
TC_026 | TS_05 | Admin Signup | Verify Phone Number is mandatory | On Admin Signup form | 1. Leave Phone Number blank 2. Click Register | Phone: '' (empty) | Mandatory field error message shown; account not created | Mandatory field error message not shown; but account not created due to disabled of Register button | Pass | High | Negative |  | Vignesh J | 2026-08-26 | Underlying validation rule is enforced via disabled Register button rather than an inline error message; account is not created with invalid/missing data, so the acceptance criterion is met. Reclassified from Fail to Pass on review, consistent with TC_041/TC_044/TC_104.
TC_027 | TS_06 | Admin Signup | Verify Email accepts a valid gmail.com address | On Admin Signup form | 1. Enter a valid gmail.com email 2. Click Register | Email: arjun.kumar@gmail.com | Field accepts the value | Field accepts the value | Pass | High | Functional |  | Vignesh J | 2026-08-26
TC_028 | TS_06 | Admin Signup | Verify Email accepts a valid hotmail.com address | On Admin Signup form | 1. Enter a valid hotmail.com email 2. Click Register | Email: arjun.kumar@hotmail.com | Field accepts the value | Field accepts the value | Pass | Medium | Functional |  | Vignesh J | 2026-08-26
TC_029 | TS_06 | Admin Signup | Verify Email accepts a valid yahoo.com address | On Admin Signup form | 1. Enter a valid yahoo.com email 2. Click Register | Email: arjun.kumar@yahoo.com | Field accepts the value | Field accepts the value | Pass | Medium | Functional |  | Vignesh J | 2026-08-26
TC_030 | TS_06 | Admin Signup | Verify Email rejects an unsupported/invalid domain (negative) | On Admin Signup form | 1. Enter an email with an invalid domain 2. Click Register | Email: 'test@xyz' | Validation error shown; account not created | Validation error shown; account not created | Pass | High | Negative |  | Vignesh J | 2026-08-26
TC_031 | TS_06 | Admin Signup | Verify Email rejects a value missing the '@' symbol | On Admin Signup form | 1. Enter an email without '@' 2. Click Register | Email: 'arjunkumargmail.com' | Validation error shown | Validation error shown | Pass | Medium | Negative |  | Vignesh J | 2026-08-26
TC_032 | TS_06 | Admin Signup | Verify Email rejects a value containing spaces | On Admin Signup form | 1. Enter an email with a space 2. Click Register | Email: 'arjun kumar@gmail.com' | Validation error shown | Validation error shown | Pass | Medium | Negative |  | Vignesh J | 2026-08-26
TC_033 | TS_06 | Admin Signup | Verify Email is mandatory | On Admin Signup form | 1. Leave Email blank 2. Click Register | Email: '' (empty) | Mandatory field error message shown; account not created | Mandatory field error message not shown; but account not created due to disabled of Register button | Pass | High | Negative |  | Vignesh J | 2026-08-26 | Underlying validation rule is enforced via disabled Register button rather than an inline error message; account is not created with invalid/missing data, so the acceptance criterion is met. Reclassified from Fail to Pass on review, consistent with TC_041/TC_044/TC_104.
TC_034 | TS_06 | Admin Signup | Verify Email rejects an already-registered address (duplicate) | An Admin account already exists with this email | 1. Enter an email already registered as Admin 2. Click Register | Email: already-registered address | Given Email Id already used | Given Email Id already used | Pass | High | Negative |  | Vignesh J | 2026-08-26
TC_035 | TS_07 | Admin Signup | Verify Password accepts exactly 6 characters (lower boundary - valid) | On Admin Signup form | 1. Enter a 6-character alphanumeric password with 1 special char & 1 uppercase 2. Click Register | Password: 'Pas@12' | Field accepts the value | Field is not accepting the value | Fail | High | Boundary Value | BUG-002 | Vignesh J | 2026-08-26
TC_036 | TS_07 | Admin Signup | Verify Password accepts exactly 10 characters (upper boundary - valid) | On Admin Signup form | 1. Enter a 10-character valid password 2. Click Register | Password: 'Password@1' | Field accepts the value | Field accepts the value | Pass | High | Boundary Value |  | Vignesh J | 2026-08-26
TC_037 | TS_07 | Admin Signup | Verify Password rejects 5 characters (below minimum - invalid) | On Admin Signup form | 1. Enter a 5-character password 2. Click Register | Password: 'Pa@12' | Validation error shown | Validation error shown | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-26
TC_038 | TS_07 | Admin Signup | Verify Password rejects 11 characters (above maximum - invalid) | On Admin Signup form | 1. Enter an 11-character password 2. Click Register | Password: 'Password@12' | Validation error shown | Field accepts the value | Fail | Medium | Boundary Value | BUG-003 | Vignesh J | 2026-08-26
TC_039 | TS_07 | Admin Signup | Verify Password rejects a value with no special character (negative) | On Admin Signup form | 1. Enter a password without a special character 2. Click Register | Password: 'Passwo1A' | Validation error shown | Validation error shown | Pass | High | Negative |  | Vignesh J | 2026-08-26
TC_040 | TS_07 | Admin Signup | Verify Password rejects a value with no uppercase letter (negative) | On Admin Signup form | 1. Enter a password without an uppercase letter 2. Click Register | Password: 'passw@1' | Validation error shown | Validation error shown | Pass | High | Negative |  | Vignesh J | 2026-08-26
TC_041 | TS_07 | Admin Signup | Verify Password is mandatory | On Admin Signup form | 1. Leave Password blank 2. Click Register | Password: '' (empty) | Mandatory field error message shown; account not created | Mandatory field error message not shown; but account not created due to disabled of Register button | Pass | High | Negative |  | Vignesh J | 2026-08-26 | Mandatory rule enforced via disabled Register button rather than inline error text; underlying acceptance criterion (no submission without password) is met. Reclassified from Fail to Pass on review.
TC_042 | TS_08 | Admin Signup | Verify Confirm Password accepts a value matching Password | On Admin Signup form | 1. Enter Password 2. Enter the identical value in Confirm Password 3. Click Register | Password & Confirm Password: 'Pass@1234' | Field accepts the value; passwords match | Field accepts the value; passwords match | Pass | High | Functional |  | Vignesh J | 2026-08-26
TC_043 | TS_08 | Admin Signup | Verify Confirm Password rejects a value that does not match Password (negative) | On Admin Signup form | 1. Enter Password 2. Enter a different value in Confirm Password 3. Click Register | Password: 'Pass@1234', Confirm: 'Pass@1243' | Validation error: passwords do not match | Validation error: passwords do not match | Pass | High | Negative |  | Vignesh J | 2026-08-26
TC_044 | TS_08 | Admin Signup | Verify Confirm Password is mandatory | On Admin Signup form | 1. Enter Password 2. Leave Confirm Password blank 3. Click Register | Confirm Password: '' (empty) | Mandatory field error message shown; account not created | Mandatory field error message not shown; but account not created due to disabled of Register button | Pass | High | Negative |  | Vignesh J | 2026-08-26 | Mandatory rule enforced via disabled Register button rather than inline error text; underlying acceptance criterion (no submission without confirm password) is met. Reclassified from Fail to Pass on review.
TC_045 | TS_09 | Admin Signup | Verify Terms & Conditions link opens the T&C page | On Admin Signup form | 1. Click the 'Terms and Conditions' link | N/A | Terms and Conditions page should be displayed | Terms and Conditions field is not present in UI | Fail | Low | Functional | BUG-004 | Vignesh J | 2026-08-26
TC_046 | TS_09 | Admin Signup | Verify form cannot be submitted without accepting Terms & Conditions (negative) | On Admin Signup form with all other fields valid | 1. Fill all fields with valid data 2. Do not check T&C 3. Click Register | T&C: unchecked | Mandatory error shown; account not created | Terms and Conditions field is not present in UI | Fail | Medium | Negative | BUG-004 | Vignesh J | 2026-08-26 | Same root cause as TC_045 — T&C field is absent from the Admin Signup form entirely, so this scenario cannot be validated as designed. Linked to BUG-004 rather than logged as a separate defect.
TC_047 | TS_10 | Admin Signup | Verify submission is blocked when Country is not selected (negative) | On Admin Signup form | 1. Fill all fields except Country 2. Click Register | Country: not selected | Mandatory field error shown | Mandatory field error message not shown; but account not created due to disabled of Register button | Pass | Medium | Negative |  | Vignesh J | 2026-08-26 | Underlying validation rule is enforced via disabled Register button rather than an inline error message; account is not created with invalid/missing data, so the acceptance criterion is met. Reclassified from Fail to Pass on review, consistent with TC_041/TC_044/TC_104.
TC_048 | TS_10 | Admin Signup | Verify submission is blocked when State is not selected (negative) | On Admin Signup form | 1. Fill all fields except State 2. Click Register | State: not selected | Mandatory field error shown | Mandatory field error message not shown; but account not created due to disabled of Register button | Pass | Medium | Negative |  | Vignesh J | 2026-08-26 | Underlying validation rule is enforced via disabled Register button rather than an inline error message; account is not created with invalid/missing data, so the acceptance criterion is met. Reclassified from Fail to Pass on review, consistent with TC_041/TC_044/TC_104.
TC_049 | TS_10 | Admin Signup | Verify submission is blocked when City is not selected (negative) | On Admin Signup form | 1. Fill all fields except City 2. Click Register | City: not selected | Mandatory field error shown | Mandatory field error message not shown; but account not created due to disabled of Register button | Pass | Medium | Negative |  | Vignesh J | 2026-08-26 | Underlying validation rule is enforced via disabled Register button rather than an inline error message; account is not created with invalid/missing data, so the acceptance criterion is met. Reclassified from Fail to Pass on review, consistent with TC_041/TC_044/TC_104.
TC_050 | TS_11 | Admin Signup | Verify submitting a completely blank form shows all mandatory errors together (negative) | On Admin Signup form | 1. Leave all fields blank 2. Click Register | N/A | All mandatory field errors are displayed simultaneously | All Mandatory fields error message not shown; but account not created due to disabled of Register button | Pass | Medium | Negative |  | Vignesh J | 2026-08-26 | Underlying validation rule is enforced via disabled Register button rather than an inline error message; account is not created with invalid/missing data, so the acceptance criterion is met. Reclassified from Fail to Pass on review, consistent with TC_041/TC_044/TC_104.
TC_051 | TS_11 | Admin Signup | Verify rapid double-click on Register does not create a duplicate account (edge case) | On Admin Signup form with valid data | 1. Fill all fields with valid data 2. Click Register button twice in quick succession | Valid signup data | Only one account is created | Only one account is created | Pass | Medium | Edge Case |  | Vignesh J | 2026-08-27
TC_052 | TS_12 | Admin Login | Verify Admin can log in successfully with valid registered credentials | A valid Admin account exists | 1. Click Login 2. Select Admin Login 3. Enter registered Email and Password 4. Click Login | Valid registered Admin credentials | Admin home page is displayed | Admin home page displayed successfully | Pass | High | Functional |  | Vignesh J | 2026-08-27
TC_053 | TS_13 | Admin Login | Verify login is rejected with an incorrect password (negative) | A valid Admin account exists | 1. Enter valid Admin email 2. Enter an incorrect password 3. Click Login | Valid email, wrong password | Error shown; user stays on Login page | Error shown; user stays on Login page | Pass | High | Negative |  | Vignesh J | 2026-08-27
TC_054 | TS_13 | Admin Login | Verify login is rejected for an unregistered email (negative) | On Admin Login form | 1. Enter an unregistered email 2. Enter any password 3. Click Login | Unregistered email | Error message shown; login rejected | Error message shown; login rejected | Pass | Medium | Negative |  | Vignesh J | 2026-08-27 | Actual Result exactly matches Expected Result — this appears to have been mis-marked as Fail. Corrected to Pass on review.
TC_055 | TS_13 | Admin Login | Verify login is rejected for an invalid email format (negative) | On Admin Login form | 1. Enter an email without a valid domain 2. Click Login | Email: 'admin@xyz' | Validation error shown | Validation error is not shown | Fail | Medium | Negative | BUG-006 | Vignesh J | 2026-08-27
TC_056 | TS_13 | Admin Login | Verify Email field is mandatory on login | On Admin Login form | 1. Leave Email blank 2. Enter Password 3. Click Login | Email: '' (empty) | Mandatory field error shown | Mandatory field error shown | Pass | High | Negative |  | Vignesh J | 2026-08-27
TC_057 | TS_13 | Admin Login | Verify Password field is mandatory on login | On Admin Login form | 1. Enter Email 2. Leave Password blank 3. Click Login | Password: '' (empty) | Mandatory field error shown | Mandatory field error shown | Pass | High | Negative |  | Vignesh J | 2026-08-27
TC_058 | TS_13 | Admin Login | Verify Login button is disabled/inert until both fields are filled | On Admin Login form | 1. Observe the Login button state with empty fields | N/A | Login button has no effect until fields are filled | Login button has no effect, validation error is shown until fields are filled | Pass | Low | Edge Case |  | Vignesh J | 2026-08-27
TC_059 | TS_13 | Admin Login | Verify Password field masks the entered characters | On Admin Login form | 1. Enter any password 2. Observe field display | Password: 'Passwordspider@12' | Characters are masked (shown as dots) | Characters are masked (shown as dots) | Pass | Low | Functional |  | Vignesh J | 2026-08-27
TC_060 | TS_13 | Admin Login | Verify login is rejected after multiple consecutive failed attempts (rate limiting / lockout check) | A valid Admin account exists | 1. Attempt login with wrong password 5 times consecutively | Valid email, wrong password x5 | Account is temporarily locked | Account is not temporarily locked, so there is no Rate Limiting | Fail | Medium | Edge Case | BUG-007 | Vignesh J | 2026-08-27 | Not an explicit requirement-doc violation (doc doesn't mandate lockout) — logged as a security observation/recommendation rather than a strict spec defect.
TC_061 | TS_14 | Merchant Signup | Verify a registered Admin email is accepted to begin Merchant signup | A valid Admin account exists | 1. Go to 'Create Merchant Login' 2. Click create account 3. Enter registered Admin email 4. Proceed | Registered admin email | 'Shopper Signup' and 'Merchant Signup' buttons are displayed | 'Shopper Signup'/'Merchant Signup' buttons displayed | Pass | High | Functional |  | Vignesh J | 2026-08-27
TC_062 | TS_14 | Merchant Signup | Verify an unregistered Admin email is rejected (negative) | On the admin-email entry screen | 1. Enter an email not registered as Admin 2. Proceed | Unregistered email | Error shown; user cannot proceed to signup | Error shown; user cannot proceed to signup | Pass | High | Negative |  | Vignesh J | 2026-08-27
TC_063 | TS_14 | Merchant Signup | Verify the Admin email field is mandatory | On the admin-email entry screen | 1. Leave email blank 2. Click Proceed | '' (empty) | Mandatory field error shown | Mandatory field error shown | Pass | Medium | Negative |  | Vignesh J | 2026-08-27
TC_064 | TS_15 | Merchant Signup | Verify User Information step accepts valid mandatory fields | On Merchant Signup, User Information step | 1. Enter valid First/Last Name, Email, Phone, Password, Gender 2. Click Next | Valid data | Step is accepted; user proceeds to Company Information | Step is accepted; user proceeds to Company Information | Pass | Medium | Functional |  | Vignesh J | 2026-08-27
TC_065 | TS_15 | Merchant Signup | Verify First Name validation (min 3 / max 20 characters) mirrors Admin Signup rule | On User Information step | 1. Enter First Name with 2 characters 2. Click Next | First Name: 'Jo' | Validation error shown | Validation error shown | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-27
TC_066 | TS_15 | Merchant Signup | Verify Email field rejects invalid domain on User Information step | On User Information step | 1. Enter an email with unsupported domain 2. Click Next | Email: 'test@xyz' | Validation error shown | Validation error shown | Pass | Medium | Negative |  | Vignesh J | 2026-08-27
TC_067 | TS_15 | Merchant Signup | Verify Phone Number rejects a number not starting with 9/8/7/6 | On User Information step | 1. Enter phone number starting with 5 2. Click Next | Phone: 5123456789 | Validation error shown | Validation error not shown | Fail | Medium | Negative | BUG-008 | Vignesh J | 2026-08-27
TC_068 | TS_15 | Merchant Signup | Verify Password field enforces 6-10 char, uppercase + special char rule | On User Information step | 1. Enter a weak password (no special char) 2. Click Next | Password: 'password1' | Validation error shown | Validation error shown | Pass | Medium | Negative |  | Vignesh J | 2026-08-27
TC_069 | TS_15 | Merchant Signup | Verify 'Next' button is disabled/blocked when a mandatory field is empty | On User Information step | 1. Leave any mandatory field empty 2. Click Next | One field empty | Step is not accepted; error(s) shown | Step is not accepted; error(s) shown | Pass | Medium | Negative |  | Vignesh J | 2026-08-27
TC_070 | TS_16 | Merchant Signup | Verify Company Name accepts a minimum of 4 alphabets | On Company Information step | 1. Enter a 4-character Company Name 2. Click Next | Company Name: 'Zeta' | Field accepts the value | Field accepts the value | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-27
TC_071 | TS_16 | Merchant Signup | Verify Company Name rejects fewer than 4 characters (negative) | On Company Information step | 1. Enter a 3-character Company Name 2. Click Next | Company Name: 'Ze' | Validation error shown | Validation error shown | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-27
TC_072 | TS_16 | Merchant Signup | Verify Company Email requires a valid domain (gmail/hotmail/yahoo) | On Company Information step | 1. Enter an invalid-domain Company Email 2. Click Next | Company Email: 'company@xyz' | Validation error shown | Validation error shown | Pass | Medium | Negative |  | Vignesh J | 2026-08-27
TC_073 | TS_16 | Merchant Signup | Verify Company Phone Number follows the same 10-digit / starting-digit rule | On Company Information step | 1. Enter a 9-digit Company Phone Number 2. Click Next | Company Phone: 987654321 | Validation error shown | Validation error shown | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-27
TC_074 | TS_16 | Merchant Signup | Verify Company GSTN rejects fewer than 6 characters (negative) | On Company Information step | 1. Enter GSTN with 4 characters 2. Click Next | GSTN: 'AB12' | Validation error shown; step not completed | Validation error shown; step not completed | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-27
TC_075 | TS_16 | Merchant Signup | Verify Company GSTN accepts alphanumeric value with minimum 6 characters (valid) | On Company Information step | 1. Enter a valid 6+ character alphanumeric GSTN 2. Click Next | GSTN: 'GST123' | Field accepts the value | Field accepts the value | Pass | Medium | Functional |  | Vignesh J | 2026-08-27
TC_076 | TS_16 | Merchant Signup | Verify Company Registration Number rejects fewer than 6 characters (negative) | On Company Information step | 1. Enter Registration Number with 4 characters 2. Click Next | Reg No.: '1234' | Validation error shown | Validation error shown | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-27
TC_077 | TS_16 | Merchant Signup | Verify Company Website requires a .com or .in domain suffix (negative) | On Company Information step | 1. Enter Company Website without .com/.in 2. Click Next | Website: 'mycompany' | Validation error shown | Validation error shown | Pass | Medium | Negative |  | Vignesh J | 2026-08-27
TC_078 | TS_16 | Merchant Signup | Verify Commission field rejects a value below the minimum 20% (negative) | On Company Information step | 1. Enter Commission as 10% 2. Click Next | Commission: 10 | Validation error shown; minimum 20% enforced | Validation error not shown; minimum 20% is not enforced | Fail | Medium | Negative | BUG-009 | Vignesh J | 2026-08-27
TC_079 | TS_16 | Merchant Signup | Verify Company Type dropdown lists all categories in the specified order | On Company Information step | 1. Click the Company Type dropdown 2. Observe list order | N/A | Beauty, Pharmacy, Grooming, Clothing, Electronic, Hardware, Furniture, Appliance, Books, Toys, Other — in order | It is in order | Pass | Low | Functional |  | Vignesh J | 2026-08-27
TC_080 | TS_16 | Merchant Signup | Verify selecting 'Others' in Company Type reveals a manual entry field (edge case) | On Company Information step | 1. Select 'Others' from Company Type dropdown | Company Type: Other | A free-text field appears to manually enter the company type | A free-text field is appeared to manually enter the company type | Pass | Medium | Edge Case |  | Vignesh J | 2026-08-27
TC_081 | TS_17 | Merchant Signup | Verify Landmark field rejects fewer than 4 characters (negative) | On Company Address step | 1. Enter Landmark with 3 characters 2. Click Finish | Landmark: 'Xyz' | Validation error shown | Validation error shown | Pass | Low | Boundary Value |  | Vignesh J | 2026-08-27
TC_082 | TS_17 | Merchant Signup | Verify Street Info field rejects fewer than 4 characters (negative) | On Company Address step | 1. Enter Street Info with 3 characters 2. Click Finish | Street: 'Xyz' | Validation error shown | Validation error shown | Pass | Low | Boundary Value |  | Vignesh J | 2026-08-27
TC_083 | TS_17 | Merchant Signup | Verify Pin Code field rejects fewer than 6 digits (negative) | On Company Address step | 1. Enter a 5-digit Pin Code 2. Click Finish | Pin Code: '60001' | Validation error shown | Validation error shown | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-27
TC_084 | TS_17 | Merchant Signup | Verify Pin Code field accepts exactly 6 digits (valid boundary) | On Company Address step | 1. Enter a 6-digit Pin Code 2. Click Finish | Pin Code: '600001' | Field accepts the value | Field accepts the value | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-27
TC_085 | TS_17 | Merchant Signup | Verify submission is blocked when Country/State/City is not selected (negative) | On Company Address step | 1. Leave Country/State/City unselected 2. Click Finish | Not selected | Mandatory field error(s) shown | Mandatory field error(s) shown | Pass | Medium | Negative |  | Vignesh J | 2026-08-27
TC_086 | TS_17 | Merchant Signup | Verify 'Back' button returns to the Company Information step without losing entered data | On Company Address step | 1. Click 'Back' | N/A | User is returned to Company Information step with previously entered data retained | User is returned to Company Information step with previously entered data retained | Pass | Low | Edge Case |  | Vignesh J | 2026-08-27
TC_087 | TS_18 | Merchant Signup | Verify Merchant account is created after completing all 3 steps and clicking Finish | All 3 signup steps completed with valid data | 1. Complete User Information 2. Complete Company Information 3. Complete Company Address 4. Accept T&C 5. Click Finish | Valid data across all 3 steps | Merchant account is created; confirmation/redirect is shown | No response after clicking Finish; account is not created. It shows Finish button with no bound handler and no console error. | Fail | High | Functional | BUG-001 | Vignesh J | 2026-08-27 | Blocker — blocks TC-089/TC-090/all Add-Edit Product cases
TC_088 | TS_19 | Merchant Login | Verify login is rejected for an invalid email format (negative) | On Merchant Login form | 1. Enter an email without a valid domain 2. Enter any password 3. Click Login | Email: 'merchant@xyz' | Validation error shown; login rejected | Validation error is not shown | Fail | Medium | Negative | BUG-006 | Vignesh J | 2026-08-27
TC_089 | TS_19 | Merchant Login | Verify login is rejected when password doesn't meet complexity rules (negative) | On Merchant Login form | 1. Enter valid Merchant email 2. Enter a password without uppercase/special char 3. Click Login | Password: 'abcdef1' | Login is rejected with an invalid-credentials error; password composition is not validated at Login. | Password field accepts the weak-composition string with no format restriction, but login correctly fails at credential-check stage since no matching Merchant account exists. | Pass | Medium | Negative |  | Vignesh J | 2026-08-27 | Reclassified from Fail to Pass on review. Composition/complexity validation is a Signup-time concern only; Login fields should accept any typed string and simply check it against the stored password.
TC_090 | TS_19 | Merchant Login | Verify Email field is mandatory on Merchant Login | On Merchant Login form | 1. Leave Email blank 2. Click Login | '' (empty) | Mandatory field error shown | Mandatory field error shown | Pass | Medium | Negative |  | Vignesh J | 2026-08-27
TC_091 | TS_19 | Merchant Login | Verify Password field is mandatory on Merchant Login | On Merchant Login form | 1. Leave Password blank 2. Click Login | '' (empty) | Mandatory field error shown | Mandatory field error shown | Pass | Medium | Negative |  | Vignesh J | 2026-08-27
TC_092 | TS_20 | Merchant Login | Verify successful login with valid Merchant credentials navigates to the Merchant home page | A valid Merchant account exists | 1. Enter valid Merchant email/password 2. Click Login | Valid Merchant credentials | Merchant home page is displayed; Add Product option shown if Admin-approved | Cannot be executed — no Merchant account can be created due to BUG-001 | Blocked | High | Functional | BUG-001 | Vignesh J | 2026-08-27 | Re-test once BUG-001 is fixed
TC_093 | TS_21 | Shopper Signup | Verify Shopper account is created with all valid mandatory fields | User is on Shopper Signup form | 1. Click Shopper Signup 2. Enter valid First/Last Name, Gender, Phone, Email, Password, Confirm Password 3. Accept T&C 4. Click Register | Valid shopper details | Shopper account is created successfully | Shopper account created successfully | Pass | High | Functional |  | Vignesh J | 2026-08-27
TC_094 | TS_22 | Shopper Signup | Verify First Name accepts exactly 3 / 20 alphabets (boundary - valid) | On Shopper Signup form | 1. Enter First Name at 3-char and separately 20-char boundary 2. Click Register | First Name: 'Ram' / 'Venkatasubramanianxas' | Field accepts the value at both boundaries | Field accepts the value at both boundaries | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-27
TC_095 | TS_22 | Shopper Signup | Verify First Name rejects 2 / 21 alphabets (boundary - invalid) | On Shopper Signup form | 1. Enter First Name at 2-char and 21-char 2. Click Register | First Name: 'Jo' / 'Venkatasubramanianxas' | Validation error shown for both | Validation error shown for both | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-27
TC_096 | TS_22 | Shopper Signup | Verify Last Name follows the same 3-20 character boundary rule | On Shopper Signup form | 1. Enter Last Name at 2-char (invalid) 2. Click Register | Last Name: 'Ra' | Validation error shown | Validation error shown | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-27
TC_097 | TS_22 | Shopper Signup | Verify Gender is mandatory on Shopper Signup | On Shopper Signup form | 1. Do not select Gender 2. Click Register | Not selected | Mandatory field error shown | Page enters an indefinite loading state (spinner) after clicking Register with Gender unselected. Reproduced on 3 attempts. DevTools Network and Console tabs show no failed request and no console error — the UI itself hangs with no validation message and no recovery. | Fail | Medium | Negative | BUG-005 | Vignesh J | 2026-08-27
TC_098 | TS_22 | Shopper Signup | Verify Phone Number rejects a number not starting with 9/8/7/6 | On Shopper Signup form | 1. Enter phone starting with 5 2. Click Register | Phone: 5123456789 | Validation error shown | Validation error not shown | Fail | High | Negative | BUG-008 | Vignesh J | 2026-08-27
TC_099 | TS_22 | Shopper Signup | Verify Phone Number rejects fewer than 10 digits (boundary - invalid) | On Shopper Signup form | 1. Enter a 9-digit phone number 2. Click Register | Phone: 987654321 | Validation error shown | Validation error shown | Pass | Medium | Boundary Value |  | Vignesh J | 2026-08-27
TC_100 | TS_22 | Shopper Signup | Verify Email field rejects an unsupported domain (negative) | On Shopper Signup form | 1. Enter an email without gmail/hotmail/yahoo domain 2. Click Register | Email: 'test@xyz' | Validation error shown; account not created | Validation error shown; account not created | Pass | High | Negative |  | Vignesh J | 2026-08-27
TC_101 | TS_22 | Shopper Signup | Verify Email field rejects a value containing spaces (negative) | On Shopper Signup form | 1. Enter an email containing a space 2. Click Register | Email: 'ravi kumar@gmail.com' | Validation error shown | Validation error shown | Pass | Medium | Negative |  | Vignesh J | 2026-08-27
TC_102 | TS_22 | Shopper Signup | Verify Password enforces the 6-10 char, uppercase + special char rule | On Shopper Signup form | 1. Enter a password missing uppercase/special char 2. Click Register | Password: 'pass1234' | Validation error shown | Validation error shown | Pass | High | Negative |  | Vignesh J | 2026-08-27
TC_103 | TS_22 | Shopper Signup | Verify Confirm Password rejects a mismatched value (negative) | On Shopper Signup form | 1. Enter Password 2. Enter a different Confirm Password 3. Click Register | Password: 'Pass@123', Confirm: 'Pass@124' | Validation error: passwords do not match | Validation error: passwords do not match | Pass | High | Negative |  | Vignesh J | 2026-08-27
TC_104 | TS_22 | Shopper Signup | Verify all mandatory fields are validated when the form is submitted blank | On Shopper Signup form | 1. Leave all fields blank 2. Click Register | N/A | Mandatory field errors shown for every required field | Mandatory field errors are not shown for every required field; but register button is disabled | Pass | Medium | Negative |  | Vignesh J | 2026-08-27 | Mandatory validation enforced via disabled Register button on blank form, not via per-field inline error text. Reclassified from Fail to Pass on review.
TC_105 | TS_23 | Shopper Signup | Verify Shopper Signup is blocked without accepting Terms & Conditions | On Shopper Signup form with all other fields valid | 1. Fill all fields with valid data 2. Do not check T&C 3. Click Register | T&C: unchecked | Register button should be disabled; account not created | Register button is disabled; account not created | Pass | Medium | Negative |  | Vignesh J | 2026-08-27
TC_106 | TS_24 | Shopper Login | Verify successful login with valid Shopper credentials | A valid Shopper account exists | 1. Click Login 2. Enter registered Shopper email/password 3. Click Login | Valid registered Shopper credentials | Shopper landing page with product listing is displayed | Shopper landing page displayed successfully | Pass | High | Functional |  | Vignesh J | 2026-08-27
TC_107 | TS_25 | Shopper Login | Verify login is rejected for an unregistered email (negative) | On Shopper Login form | 1. Enter an email not registered on the app 2. Enter any password 3. Click Login | Unregistered email | Appropriate error message is displayed | Appropriate error message is displayed | Pass | Medium | Negative |  | Vignesh J | 2026-08-27
TC_108 | TS_25 | Shopper Login | Verify login is rejected with an incorrect password (negative) | A valid Shopper account exists | 1. Enter valid Shopper email 2. Enter incorrect password 3. Click Login | Valid email, wrong password | Error shown; user stays on Login page | Error shown; user stays on Login page | Pass | High | Negative |  | Vignesh J | 2026-08-27
TC_109 | TS_25 | Shopper Login | Verify login is rejected for an invalid email format (negative) | On Shopper Login form | 1. Enter an email without a valid domain 2. Click Login | Email: 'shopper@xyz' | Validation error shown | Validation error shown | Pass | Medium | Negative |  | Vignesh J | 2026-08-27
TC_110 | TS_25 | Shopper Login | Verify Email field is mandatory on Shopper Login | On Shopper Login form | 1. Leave Email blank 2. Click Login | '' (empty) | Mandatory field error shown | Mandatory field error shown | Pass | High | Negative |  | Vignesh J | 2026-08-27
TC_111 | TS_25 | Shopper Login | Verify Password field is mandatory on Shopper Login | On Shopper Login form | 1. Leave Password blank 2. Click Login | '' (empty) | Mandatory field error shown | Mandatory field error shown | Pass | High | Negative |  | Vignesh J | 2026-08-27
TC_112 | TS_25 | Shopper Login | Verify Password field masks entered characters | On Shopper Login form | 1. Enter any password 2. Observe field display | Any password | Characters are masked (dots) | Characters are masked (dots) | Pass | Low | Functional |  | Vignesh J | 2026-08-27
TC_113 | TS_25 | Shopper Login | Verify rapid double-click on Login with valid credentials does not cause duplicate session/error (edge case) | A valid Shopper account exists | 1. Enter valid credentials 2. Click Login button twice in quick succession | Valid credentials | User is logged in once cleanly; no duplicate session or error state | User is logged in once cleanly; no duplicate session or error state | Pass | Low | Edge Case |  | Vignesh J | 2026-08-27
TC_114 | TS_26 | Search Product | Verify searching a valid/existing product name via the search bar displays its description page | Shopper is logged in, on landing page | 1. Click Search Bar 2. Enter a valid product name 3. Click the Search icon | Product name: e.g. 'Cameras' | A list/grid of matching product results is displayed. User can then select an individual product from the results to open its full description page. | Search bar shows a dropdown of previously-searched terms while typing (autocomplete-like behavior it shows relevant suggestions). After clicking the Search icon, a brief loading state appears, followed by a flash of "Sorry No Data Found" (large text with image) for roughly 0.5 seconds, before the correct list of matching results is displayed. | Fail | High | Functional | BUG-010 | Vignesh J | 8-28-2026 | Expected Result corrected to reflect actual app flow (results list, not a direct single product page) — confirmed by tester. Autocomplete dropdown noted separately, not treated as a defect pending confirmation of suggestion relevance.
TC_115 | TS_26 | Search Product | Verify the Search icon (not just typing) is required to trigger the search | Shopper is on landing page | 1. Click Search Bar 2. Type a valid product name 3. Observe if results appear before clicking the Search icon | Product name: mobiles | Search executes only after the Search icon is clicked | Search executes only after the Search icon is clicked | Pass | Medium | Functional |  | Vignesh J | 8-28-2026
TC_116 | TS_27 | Search Product | Verify searching for a non-existent product shows no matching results (negative) | Shopper is on landing page | 1. Click Search Bar 2. Enter a random unmatched string 3. Click Search icon | Search text: 'zzzxxxyyy123' | Sorry No Data Found' message is shown | Sorry No Data Found' message is shown | Pass | Medium | Negative |  | Vignesh J | 8-28-2026
TC_117 | TS_27 | Search Product | Verify submitting an empty search query is handled gracefully (negative) | Shopper is on landing page | 1. Click Search Bar 2. Leave it blank 3. Click Search icon | Search text: '' (empty) | No crash/error; either full catalog or a prompt to enter a search term is shown | with an empty data and clicked search icon, it loaded a page, and it shows a similar to home page but it is irrelevant | Fail | Low | Negative | BUG-011 | Vignesh J | 8-28-2026
TC_118 | TS_27 | Search Product | Verify search accepts a single-character query (minimum length boundary) | Shopper is on landing page | 1. Enter a single character in Search Bar 2. Click Search icon | Search text: 'a' | Matching results (if any) are shown without error | Matching results (if any) are shown without error | Pass | Low | Boundary Value |  | Vignesh J | 8-28-2026
TC_119 | TS_27 | Search Product | Verify search is case-insensitive | Shopper is on landing page | 1. Search a product name in all uppercase 2. Repeat in all lowercase 3. Compare results | Search text: 'SHOES' vs 'shoes' | Both searches return the same matching results | Both searches didn't returned the same matching results | Fail | Medium | Edge Case | BUG-012 | Vignesh J | 8-28-2026
TC_120 | TS_27 | Search Product | Verify search input handles special characters / script-like input safely (negative security check) | Shopper is on landing page | 1. Enter a string containing special/SQL-like characters 2. Click Search icon | Search text: "' OR 1=1 --" | Input is safely handled/escaped; no error page, no unexpected data exposure | Input is safely handled/escaped; no error page, no unexpected data exposure | Pass | High | Negative |  | Vignesh J | 8-28-2026
TC_121 | TS_28 | Search Product | Verify browsing a category from the landing page shows the correct product list | Shopper is on landing page | 1. Scroll to product categories 2. Select a category | Any listed category | Product list for the selected category is displayed | Product list for the selected category is displayed | Pass | Medium | Functional |  | Vignesh J | 8-28-2026
TC_122 | TS_28 | Search Product | Verify selecting a product from category listing opens the correct product description page | Category product list is displayed | 1. Select a product from the category listing | Any listed product | Product description page for the selected item is displayed | Product description page for the selected item is displayed | Pass | Medium | Functional |  | Vignesh J | 8-28-2026
TC_123 | TS_28 | Search Product | Verify all category tiles load correctly on the landing page (UI check) | Shopper is on landing page | 1. Scroll down to the categories section 2. Observe all category tiles | N/A | All category tiles render with correct labels/images | All category tiles render with correct labels/images | Pass | Low | Functional |  | Vignesh J | 8-28-2026
TC_124 | TS_28 | Search Product | Verify search results only include genuinely matching products (no irrelevant results) | Shopper is on landing page | 1. Search for a specific product name 2. Review all returned results | Search text: 'watches' | All returned results shown for the searched term | All returned results shown for the searched term | Pass | Medium | Functional |  | Vignesh J | 8-28-2026
TC_125 | TS_27 | Search Product | Verify search with only whitespace input does not return arbitrary/all results (negative) | Shopper is on landing page | 1. Enter only spaces in the Search Bar 2. Click Search icon | Search text: ' ' (spaces only) | Treated as empty/invalid input; not treated as a valid search term (a 'No Data Found' state is an acceptable outcome, consistent with TC_126) | Sorry No Data Found' page is shown | Pass | Low | Negative |  | Vignesh J | 8-28-2026 | Reclassified from Fail to Pass — showing 'No Data Found' for a whitespace-only query is consistent with how the same message is treated as an acceptable outcome in TC_126. Expected Result reworded to reflect this.
TC_126 | TS_27 | Search Product | Verify search accepts a very long query string without breaking the UI (boundary) | Shopper is on landing page | 1. Enter a 50+ character string in Search Bar 2. Click Search icon | Search text: 50+ character string | UI does not break or overflow; either results or No data found page shown gracefully | 'Sorry No Data Found' page is shown | Pass | Low | Boundary Value |  | Vignesh J | 8-29-2026
TC_127 | TS_29 | Add to Cart | Verify 'ADD TO CART' from the product description page (search flow) adds the product | Shopper has opened a product via search | 1. On product description page, click 'ADD TO CART' | Any available product | Button label changes to 'Added' | Button label changed to 'Added' | Pass | High | Functional |  | Vignesh J | 8-29-2026
TC_128 | TS_29 | Add to Cart | Verify cart item count increments by 1 after adding a product via the search flow | Product just added to cart via search flow | 1. Observe the cart icon behavior in the cart page | N/A | Cart item quantity count increases by 1 | Cart item quantity count is increasing by 1 | Pass | High | Functional |  | Vignesh J | 8-29-2026
TC_129 | TS_30 | Add to Cart | Verify 'ADD TO CART' from the category/landing page listing adds the product | Shopper has opened a product via category listing | 1. On product description page (reached via category), click 'ADD TO CART' | Any available product | Button label changes to 'Added' | Button label changed to 'Added' | Pass | Medium | Functional |  | Vignesh J | 8-29-2026
TC_130 | TS_30 | Add to Cart | Verify cart item count increments by 1 correctly when adding from the category flow | Product just added to cart via category flow | 1. Observe the cart icon behavior in the cart page | N/A | Cart item quantity count increases by 1 | Cart item quantity count increases by 1 | Pass | Medium | Functional |  | Vignesh J | 8-29-2026
TC_131 | TS_31 | Add to Cart | Verify clicking 'Added' again does not add a duplicate entry (edge case) | A product has already been added to cart (button shows 'Added') | 1. Click the 'Added' button again | Same product, already in cart | Cart count does not increase further; no duplicate line item is created | Cart count were not increase further | Pass | Medium | Edge Case |  | Vignesh J | 8-29-2026
TC_132 | TS_31 | Add to Cart | Verify adding multiple different products updates the cart count cumulatively | Cart is empty | 1. Add 3 different products to cart from different pages | 3 distinct products | Cart items count equals 3 | Cart items count equals 3 | Pass | Medium | Functional |  | Vignesh J | 8-29-2026
TC_133 | TS_31 | Add to Cart | Verify rapid double-click on 'ADD TO CART' does not add the product twice (edge case) | Shopper is on a product description page | 1. Click 'ADD TO CART' twice in quick succession | Any available product | Product is added only once; cart count increases by exactly 1 | Product is added only once; cart count increases by exactly 1 | Pass | High | Edge Case |  | Vignesh J | 8-29-2026
TC_134 | TS_31 | Add to Cart | Verify the Cart page lists all added products with correct name and price | Multiple products have been added to cart | 1. Click the Cart icon 2. Review the listed products | Products previously added | Cart page lists every added product with correct name, price and quantity | Cart page lists every added product with correct name, price and quantity | Pass | High | Functional |  | Vignesh J | 8-29-2026
TC_135 | TS_31 | Add to Cart | Verify removing a product from the cart updates the listing and count (negative/functional) | A product exists in the cart | 1. Open Cart 2. Remove a product from the list by clicking remove item button | Any product in cart | Product no longer appears in cart; cart count decrements accordingly | Product no longer appears in cart; cart count decrements accordingly | Pass | Medium | Functional |  | Vignesh J | 8-29-2026
TC_136 | TS_31 | Add to Cart | Verify that a product with a quantity of one is removed from the cart when the minus (-) button is clicked. | A product exists in the cart | 1. Open Cart 2. Remove a product from the list by clicking (-) button | Any product in cart | Clicking the minus (-) button on a quantity-1 item decrements it to 0 and removes the product from the cart; cart count updates accordingly | Clicking the minus (-) button on a quantity-1 item does not remove the product or decrement the cart count | Fail | Medium | Functional | BUG-013 | Vignesh J | 8-29-2026
TC_137 | TS_31 | Add to Cart | Verify adding a large quantity of the same product is handled without error (boundary) | Shopper is on a product description page | 1. Increase quantity to a large number (e.g. 14) 2. Add to cart | Quantity: 14 | Cart accepts and reflects the quantity correctly | Cart accepts and reflects the quantity correctly | Pass | Low | Boundary Value |  | Vignesh J | 8-29-2026
TC_138 | TS_31 | Add to Cart | Verify adding the same product via both search and landing-page paths does not create duplicate cart entries | Cart is empty | 1. Add a product via search flow 2. Navigate to the same product via category listing 3. Add to cart again | Same product via two different navigation paths | Cart shows a single line item with quantity 2 (or increments existing entry), not two separate entries | Cart shows a single line item with quantity 2 not two separate entries | Pass | Medium | Edge Case |  | Vignesh J | 8-29-2026
TC_139 | TS_31 | Add to Cart | Verify cart total price updates correctly as products are added | Cart is empty | 1. Add Product A 2. Note cart total 3. Add Product B 4. Recheck cart total | Two products with known prices | Cart total equals the sum of added products' prices at each step | Cart total equals the sum of added products prices at each step | Pass | Medium | Functional |  | Vignesh J | 8-29-2026
TC_140 | TS_31 | Add to Cart | Verify the Cart page does not error out when accessed with an empty cart | Cart is empty (no products added) | 1. Click the Cart icon with no products added | N/A | 'Cart is empty' or equivalent message is shown; no error/crash | Cart is empty' page is shown; no error/crash | Pass | Low | Negative |  | Vignesh J | 8-29-2026
TC_141 | TS_32 | Buy Product | Verify 'BUY NOW' on the product description page navigates to Select Delivery Address | Shopper has opened a product's description page | 1. Click 'BUY NOW' | Any available product | User is navigated to the 'SELECT A DELIVERY ADDRESS' page | User is navigated to the 'SELECT A DELIVERY ADDRESS' page | Pass | High | Functional |  | Vignesh J | 8-29-2026
TC_142 | TS_33 | Buy Product | Verify 'BUY NOW' from the Cart page navigates to Select Delivery Address | A product exists in the cart | 1. Open Cart 2. Click 'BUY NOW' on a listed product | A product already in cart | User is navigated to the 'SELECT A DELIVERY ADDRESS' page | User is navigated to the 'SELECT A DELIVERY ADDRESS' page | Pass | High | Functional |  | Vignesh J | 8-29-2026
TC_143 | TS_33 | Buy Product | Verify the Cart icon in the top-right corner opens the Cart page correctly | Shopper is on any page post-login | 1. Click the Cart icon at top-right corner | N/A | Cart page is displayed with current cart contents | Cart page is displayed with current cart contents | Pass | Medium | Functional |  | Vignesh J | 8-29-2026
TC_144 | TS_33 | Buy Product | Verify 'BUY NOW' is unavailable or disabled when the cart is empty (negative) | Cart is empty | 1. Open Cart page with no items 2. Look for 'BUY NOW' option | N/A | BUY NOW' should not perform any functionality when there is nothing to purchase | 'BUY NOW' should not perform any functionality when there is nothing to purchase | Pass | Medium | Negative |  | Vignesh J | 8-29-2026
TC_145 | TS_33 | Buy Product | Verify rapid double-click on 'BUY NOW' does not trigger duplicate checkout navigation (edge case) | A product exists in the cart | 1. Click 'BUY NOW' twice in quick succession | A product in cart | User is navigated to Select Delivery Address once; no duplicate session/page state | User is navigated to Select Delivery Address once; no duplicate session/page state | Pass | Medium | Edge Case |  | Vignesh J | 8-29-2026
TC_146 | TS_34 | Buy Product | Verify the product carried into Select Delivery Address matches the one selected | Shopper clicks 'BUY NOW' on a specific product | 1. Click 'BUY NOW' on Product X 2. On Select Delivery Address / order summary, verify the product shown | A specific known product | The correct product (name/price) is reflected on the subsequent checkout step | The correct product (name/price) is reflected on the subsequent checkout step | Pass | High | Functional |  | Vignesh J | 8-29-2026
TC_147 | TS_34 | Buy Product | Verify navigating back from Select Delivery Address preserves cart/product state | Shopper is on Select Delivery Address page | 1. Click the browser/app Back action 2. Return to Cart or Product page | N/A | Cart contents and product state remain intact; nothing is lost or duplicated | Cart contents and product state remain intact; nothing is lost or duplicated | Pass | Low | Edge Case |  | Vignesh J | 8-29-2026
TC_148 | TS_35 | Search Product | Verify selecting a product from the search results list navigates to its description page | Shopper has performed a search that returned a results list | 1. Perform a valid product search 2. On the results list/grid, click a specific product | Any product from the results list | The selected product's full description page is displayed (image, price, Add to Cart/Buy Now) | The selected product's full description page is displayed (image, price, Add to Cart/Buy Now) | Pass | High | Functional |  | Vignesh J | 8-29-2026
TC_149 | TS_36 | Add Address | Verify a new address is added successfully with all valid mandatory fields | Shopper has clicked 'Buy Now' and reached Select Delivery Address | 1. Click 'Add New Address' 2. Select Address type 3. Fill Name, House/Office Info, Street, Landmark, Country/State/City, Pin Code, Phone Number 4. Click 'Add Address' | Valid address data (Address 1 — deliverable): Name: Rohan ¦ Type: Home ¦ House/Office Info: Near ICM ¦ Street: Tark street ¦ Landmark: Balnet ¦ City: Pune ¦ Pincode: 432102 ¦ State: Maharashtra ¦ Country: India ¦ Phone: 7654789065 | Successfully Added' message is displayed | 'Successfully Added' message is displayed | Pass | High | Functional |  | Vignesh J | 8-29-2026
TC_150 | TS_37 | Add Address | Verify Name field accepts the 3-20 character valid boundary | On Add Address form | 1. Enter Name at 3-char and separately 20-char length 2. Click 'Add Address' | Name: 'Raj' / 'Venkatasubramanianxa' | Field accepts the value at both boundaries | Field accepts the value at both boundaries | Pass | Medium | Boundary Value |  | Vignesh J | 8-29-2026
TC_151 | TS_37 | Add Address | Verify Name field rejects the 2/21 character invalid boundary | On Add Address form | 1. Enter Name at 2-char and 21-char length 2. Click 'Add Address' | Name: 'Ra' / 'Venkatasubramanianxaa' | Validation error shown for both | Validation error shown for both | Pass | Medium | Boundary Value |  | Vignesh J | 8-29-2026
TC_152 | TS_37 | Add Address | Verify Name field is mandatory | On Add Address form | 1. Leave Name blank 2. Click 'Add Address' | Name: '' (empty) | Mandatory field error shown; address not saved | Mandatory field error shown; address not saved | Pass | Medium | Negative |  | Vignesh J | 8-29-2026
TC_153 | TS_37 | Add Address | Verify House/Office Info field is mandatory | On Add Address form | 1. Leave House/Office Info blank 2. Click 'Add Address' | '' (empty) | Mandatory field error shown; address not saved | Mandatory field error shown; address not saved | Pass | Medium | Negative |  | Vignesh J | 8-29-2026
TC_154 | TS_37 | Add Address | Verify Street Info field is mandatory | On Add Address form | 1. Leave Street Info blank 2. Click 'Add Address' | '' (empty) | Mandatory field error shown; address not saved | Mandatory field error shown; address not saved | Pass | Medium | Negative |  | Vignesh J | 8-29-2026
TC_155 | TS_37 | Add Address | Verify Landmark field is mandatory | On Add Address form | 1. Leave Landmark blank 2. Click 'Add Address' | '' (empty) | Mandatory field error shown; address not saved | Mandatory field error shown; address not saved | Pass | Medium | Negative |  | Vignesh J | 8-29-2026
TC_156 | TS_38 | Add Address | Verify the (i) icon displays serviceable pincode information before entering Pin Code | On Add Address form | 1. Click the (i) icon next to Pin Code field | N/A | Serviceability info listing valid delivery pincodes is displayed | Serviceability info listing valid delivery pincodes is displayed | Pass | Medium | Functional |  | Vignesh J | 8-29-2026
TC_157 | TS_38 | Add Address | Verify Pin Code field rejects fewer than 6 digits (boundary - invalid) | On Add Address form | 1. Enter a 5-digit Pin Code 2. Click 'Add Address' | Pin Code: '60001' | Validation error shown; address not saved | Validation error shown; address not saved | Pass | Medium | Boundary Value |  | Vignesh J | 8-29-2026
TC_158 | TS_38 | Add Address | Verify Pin Code field accepts exactly 6 digits (boundary - valid) | On Add Address form | 1. Enter a valid 6-digit, serviceable Pin Code 2. Click 'Add Address' | Pin Code: 432102 (Address 1 — confirmed deliverable) | Field accepts the value; address is saved | Field accepts the value; address is saved | Pass | Medium | Boundary Value |  | Vignesh J | 8-29-2026
TC_159 | TS_38 | Add Address | Verify a non-serviceable pincode is rejected (per the (i) icon's listed pincodes) | On Add Address form, a known non-serviceable 6-digit pincode is available | 1. Enter a 6-digit pincode not on the serviceable list 2. Click 'Add Address' | Pin Code: 110001 (New Delhi — not in the deliverable pincode list: 432101-432106, 560010) | Error indicating delivery is not available to this pincode; address not saved | The error did not indicate that delivery is not available to this pincode; address saved | Fail | Medium | Negative | BUG-014 | Vignesh J | 8-29-2026
TC_160 | TS_40 | Add Address | Verify Phone Number is rejected if it doesn't start with 9/8/7/6 on Add Address | On Add Address form | 1. Enter a 10-digit phone number starting with 5 2. Click 'Add Address' | Phone: 5123456789 | Validation error shown; field rejected | Validation error is not shown; field accepts the value | Fail | Medium | Negative | BUG-008 | Vignesh J | 8-29-2026 | Same root cause as BUG-008 (Merchant/Shopper Signup) — phone starting-digit validation gap also present on Add Address. Linked rather than duplicated.
TC_161 | TS_40 | Add Address | Verify Phone Number is mandatory on Add Address | On Add Address form | 1. Leave Phone Number blank 2. Click 'Add Address' | '' (empty) | Mandatory field error shown | Mandatory field functionality woks | Pass | Medium | Negative |  | Vignesh J | 8-29-2026
TC_162 | TS_39 | Add Address | Verify submission is blocked when Country/State/City is not selected | On Add Address form | 1. Leave Country/State/City unselected 2. Click 'Add Address' | Not selected | Mandatory field error shown | Mandatory field functionality woks | Pass | Medium | Negative |  | Vignesh J | 8-29-2026
TC_163 | TS_39 | Add Address | Verify Address Type radio button selection is mandatory | On Add Address form | 1. Do not select an Address Type 2. Fill remaining fields 3. Click 'Add Address' | Not selected | Mandatory field error shown; address not saved | Mandatory field functionality woks | Pass | Low | Negative |  | Vignesh J | 8-29-2026
TC_164 | TS_41 | Add Address | Verify multiple saved addresses can be added and one can be selected during checkout | Shopper has at least one saved address already | 1. Add a second address 2. Return to Select Delivery Address 3. Choose between the two saved addresses | Address 1 (Pune): Name: Rohit ¦ Type: Home ¦ House/Office Info: Near ICC ¦ Street: Cricket street ¦ Landmark: Batting style ¦ City: Pune ¦ Pincode: 432102 ¦ State: Maharashtra ¦ Country: India ¦ Phone: 7654789065 // Address 2 (Ahmednagar): Name: Vikky ¦ Type: Home ¦ House/Office Info: Gill ¦ Street: GST ¦ Landmark: Gill ¦ City: Ahmednagar ¦ Pincode: 432106 ¦ State: Maharashtra ¦ Country: India ¦ Phone: 7890678909 | Both addresses are listed; either can be selected for delivery | Both addresses are listed; | Pass | Low | Edge Case |  | Vignesh J | 8-29-2026
TC_165 | TS_42 | Place Order | Verify Net Banking can be selected as a payment method on the Payment Method page | Shopper is on the Payment Method page (payment-options) | 1. Select the 'Net Banking' radio button 2. Click Proceed | N/A | User proceeds to bank selection | User proceeds to bank selection | Pass | Medium | Functional |  | Vignesh J | 8-29-2026
TC_166 | TS_42 | Place Order | Verify a Debit Card is added successfully via the 'Add Card' modal with valid details | Shopper is on the Payment Method page | 1. Click 'Add Card' 2. Enter Card Holder Name, Card Number, PIN, Expiry Month, Expiry Year, CVV 3. Select the 'Debit' radio button 4. Click 'Add' | Bank: IDHC Bank ¦ Card Holder Name: Vikky ¦ Card Number: 7445789612379999 ¦ CVV: 378 ¦ PIN: 8191 ¦ Expiry: 08/31 | Card is added successfully and becomes available as a selectable payment option | Card is added successfully and becomes available as a selectable payment option | Pass | Medium | Functional |  | Vignesh J | 8-29-2026
TC_167 | TS_42 | Place Order | Verify a Credit Card is added successfully via the 'Add Card' modal with valid details | Shopper is on the Payment Method page | 1. Click 'Add Card' 2. Enter Card Holder Name, Card Number, PIN, Expiry Month, Expiry Year, CVV 3. Select the 'Credit' radio button 4. Click 'Add' | Bank: IDHC Bank ¦ Card Holder Name: Vikky ¦ Card Number: 7445789612380000 ¦ CVV: 880 ¦ PIN: 4369 ¦ Expiry: 08/31 | Card is added successfully and becomes available as a selectable payment option | Card is added successfully and becomes available as a selectable payment option | Pass | Medium | Functional |  | Vignesh J | 8-29-2026
TC_168 | TS_42 | Place Order | Verify 'Add Card' is blocked when mandatory fields are left empty (negative) | Add Card' page is open | 1. Leave one or more mandatory fields blank (Card Holder Name/Card Number/PIN/Expiry Month/Expiry Year/CVV) 2. Select Debit or Credit 3. Click 'Add' | One or more fields left empty | Mandatory field error(s) shown; card is not added | Mandatory field error(s) shown; card is not added | Pass | Low | Negative |  | Vignesh J | 8-29-2026
TC_169 | TS_43 | Place Order | Verify an order is placed successfully via Cash on Delivery (COD) | Shopper has a product in cart/buy-now flow and a valid address selected | 1. Select saved address 2. Click Proceed 3. Select COD radio button 4. Click Proceed | Address used: Name: Rohit ¦ Type: Home ¦ House/Office Info: Near ICC ¦ Street: Cricket street ¦ Landmark: Batting style ¦ City: Pune ¦ Pincode: 432102 ¦ State: Maharashtra ¦ Country: India ¦ Phone: 7654789065, Payment: COD | Order confirmation page with success banner is displayed | Order confirmation page with success banner is displayed | Pass | High | Functional |  | Vignesh J | 8-29-2026
TC_170 | TS_43 | Place Order | Verify 'Proceed' is blocked if no delivery address is selected (negative) | Shopper is on Select Delivery Address page with a saved address available but unselected | 1. Do not select any address 2. Click Proceed | No address selected | User is prompted to select an address; unable to proceed | User is prompted to select an address; unable to proceed | Pass | Medium | Negative |  | Vignesh J | 8-29-2026
TC_171 | TS_44 | Place Order | Verify an order is placed successfully via Net Banking | Shopper has a valid address selected | 1. Select Net Banking 2. Click Proceed 3. Select bank 4. Click Submit 5. Enter valid User ID/Password on bank login page 6. Click Submit | Address used: Name: Vikky ¦ Type: Home ¦ House/Office Info: Gill ¦ Street: GST ¦ Landmark: Gill ¦ City: Ahmednagar ¦ Pincode: 432106 ¦ State: Maharashtra ¦ Country: India ¦ Phone: 7890678909, Payment: Net Banking | Order confirmation page with success banner is displayed | Order confirmation page with success banner is displayed | Pass | High | Functional |  | Vignesh J | 8-29-2026
TC_172 | TS_44 | Place Order | Verify Net Banking login fails gracefully with incorrect User ID/Password (negative) | Shopper is on the Net Banking login page during checkout | 1. Enter an incorrect User ID or Password 2. Click Submit | Invalid Net Banking credentials | Error shown; payment not completed; user remains on/returns to login step | Invalid Net Banking credentials shown | Pass | Medium | Negative |  | Vignesh J | 8-29-2026
TC_173 | TS_45 | Place Order | Verify an order is placed successfully via Debit Card | Shopper has a valid deliverable address selected and has added a Debit Card via 'Add Card' (see TC_166) | 1. On Payment Method page, select the added Debit Card 2. Click Proceed 3. Confirm/enter any final payment step if prompted | Bank: IDHC Bank ¦ Card Holder Name: Vikky ¦ Card Number: 7445789612379999 ¦ CVV: 378 ¦ PIN: 8191 ¦ Expiry: 08/31 ¦ Delivery Address: Karthi, Mysuru - 560010 | Order confirmation page with success banner is displayed | Order confirmation page with success banner is displayed | Pass | High | Functional |  | Vignesh J | 8-29-2026
TC_174 | TS_45 | Place Order | Verify Debit Card payment rejects an invalid/incomplete card number (negative/boundary) | Shopper is on the Debit Card payment step | 1. Enter a card number with fewer than the required digits 2. Click Submit/Pay | Incomplete card number (e.g. 6 digits) | Validation error shown; payment not processed | Validation error shown; payment not processed | Pass | Medium | Boundary Value |  | Vignesh J | 8-29-2026
TC_175 | TS_45 | Place Order | Verify Debit Card payment rejects an expired expiry date (negative) | Shopper is on the Debit Card payment step | 1. Enter a card expiry date in the past 2. Click Submit/Pay | Expiry: a past month/year | Validation error indicating the card has expired; payment not processed | Validation error indicating the card has expired; payment not processed | Pass | Medium | Negative |  | Vignesh J | 8-29-2026
TC_176 | TS_45 | Place Order | Verify Debit Card payment rejects an invalid CVV (wrong digit count) (negative/boundary) | Shopper is on the Debit Card payment step | 1. Enter a 2-digit CVV instead of 3 2. Click Submit/Pay | CVV: '12' | Validation error shown; payment not processed | Validation error shown; payment not processed | Pass | Medium | Boundary Value |  | Vignesh J | 8-29-2026
TC_177 | TS_46 | Place Order | Verify an order is placed successfully via Credit Card | Shopper has a valid deliverable address selected and has added a Credit Card via 'Add Card' (see TC_167) | 1. On Payment Method page, select the added Credit Card 2. Click Proceed 3. Confirm/enter any final payment step if prompted | Bank: IDHC Bank ¦ Card Holder Name: Vikky ¦ Card Number: 7445789612380000 ¦ CVV: 880 ¦ PIN: 4369 ¦ Expiry: 08/31 ¦ Delivery Address: Rohit, Pune - 432102 | Order confirmation page with success banner is displayed | Order confirmation page with success banner is displayed | Pass | High | Functional |  | Vignesh J | 8-29-2026
TC_178 | TS_46 | Place Order | Verify Credit Card payment rejects an invalid/incomplete card number (negative/boundary) | Shopper is on the Credit Card payment step | 1. Enter a card number with fewer than the required digits 2. Click Submit/Pay | Incomplete card number | Validation error shown; payment not processed | Validation error shown; payment not processed | Pass | Medium | Boundary Value |  | Vignesh J | 8-29-2026
TC_179 | TS_46 | Place Order | Verify Credit Card CVV field is mandatory | Shopper is on the Credit Card payment step | 1. Leave CVV blank 2. Click Submit/Pay | CVV: '' (empty) | Mandatory field error shown; payment not processed | Mandatory field error shown; payment not processed | Pass | Medium | Negative |  | Vignesh J | 8-29-2026
TC_180 | TS_47 | Place Order | Verify rapid double-click on 'Proceed'/'Place Order' does not create a duplicate order (duplicate-order prevention) | Shopper has completed address and payment selection | 1. Click 'Proceed'/final order-placing button twice in quick succession | Valid address and payment details, COD for simplicity | Only one order is created; no duplicate order/charge occurs | Only one order is created; no duplicate order/charge occurs | Pass | High | Edge Case |  | Vignesh J | 8-29-2026
TC_181 | TS_47 | Place Order | Verify navigating back after a successful order does not allow resubmission of the same order (edge case) | Shopper has just completed an order successfully | 1. Click browser/app Back after order confirmation 2. Attempt to resubmit via Back-cached page state | N/A | Resubmission is blocked or leads to a fresh state; no duplicate order is created | Resubmission is blocked or leads to a fresh state; no duplicate order is created | Pass | Medium | Edge Case |  | Vignesh J | 8-29-2026
TC_182 | TS_47 | Place Order | Verify the order confirmation page displays correct order details | An order has just been placed successfully | 1. Review the order confirmation page | Order placed using one of the 3 confirmed deliverable addresses (Pune/Ahmednagar/Mysuru) — verify against the specific address+payment combo actually used | Correct product, delivery address, and payment method are reflected on the confirmation page | Correct product, delivery address, and payment method are reflected on the confirmation page | Pass | High | Functional |  | Vignesh J | 8-29-2026
TC_183 | TS_47 | Place Order | Verify payment method selection is mandatory before Proceed (negative) | Shopper is on the Select a Payment Method page | 1. Do not select any payment method 2. Click Proceed | No payment method selected | User is prompted to select a payment method; unable to proceed | User is prompted to select a payment method; unable to proceed | Pass | Medium | Negative |  | Vignesh J | 8-29-2026

## Defect Log
Defect ID | Module | Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Found By | Date Found | Related TC ID
BUG-001 | Merchant Signup | 'Finish' button on the Company Address step does not create the Merchant account | 1. Go to Create Merchant/Shopper 2. Enter registered Admin email > Merchant Signup 3. Complete User Information 4. Complete Company Information 5. Complete Company Address 6. Accept T&C 7. Click Finish | Merchant account should be created and a confirmation/redirect shown | No action occurs after clicking Finish. Browser console shows no errors. DOM shows <button type="submit">Finish</button> with no bound submit handler. | Blocker | High | Open |  |  | TC_087
BUG-002 | Admin Signup | Password field rejects the documented minimum length (6 characters) even when composition rules are met | 1. Go to Admin Signup 2. Enter a 6-character password meeting complexity rules (e.g. 'Pas@12') 3. Fill remaining fields 4. Click Register | Field should accept a 6-character password that meets composition rules (per requirement doc minimum) | Field rejects the value; actual enforced minimum appears to be higher (~8 characters) | Major | Medium | Open |  |  | TC_035
BUG-003 | Admin Signup | Password field accepts more than the documented maximum length (10 characters) | 1. Go to Admin Signup 2. Enter an 11-character password (e.g. 'Password@12') 3. Fill remaining fields 4. Click Register | Field should reject a password exceeding the documented 10-character maximum | Field accepts the 11-character value; account proceeds | Major | Medium | Open |  |  | TC_038
BUG-004 | Admin Signup | Terms & Conditions field/link is missing entirely from the live Admin Signup form | 1. Go to Admin Signup 2. Look for a 'Terms and Conditions' checkbox/link as listed in the requirement doc | A Terms & Conditions checkbox/link should be present and mandatory, per requirement doc section 1.1.8 | No Terms & Conditions field is present anywhere on the Admin Signup form | Medium | Medium | Open |  |  | TC_045
BUG-005 | Shopper Signup | Signup form hangs indefinitely (infinite loading spinner) when Register is clicked with Gender left unselected | 1. Go to Shopper Signup 2. Fill all fields except Gender 3. Click Register 4. Observe page state | A mandatory-field validation error should be shown for Gender; form should not submit | Page shows an indefinite loading spinner with no error message and no navigation. Reproduced on 3 separate attempts. No error visible in DevTools Console or Network tabs — UI-level hang, not a failed network call. | Major | High | Open |  |  | TC_097
BUG-006 | Admin Login / Merchant Login | Login forms do not perform client-side email format validation before attempting login | 1. Go to Admin Login (or Merchant Login) 2. Enter an email with an invalid/unsupported domain (e.g. 'admin@xyz') 3. Click Login | A client-side validation error should be shown before any login attempt is made | No validation error is shown; form allows the invalid-format email through to submission | Minor | Low | Open |  |  | TC_055, TC_088
BUG-007 | Admin Login | No account lockout or rate limiting after repeated failed login attempts | 1. Attempt Admin Login with a valid email and an incorrect password, 5 times consecutively | Account should be temporarily locked, or a CAPTCHA/warning should appear, after repeated failures | Account remains fully accessible with no lockout, delay, or warning after 5 consecutive failed attempts | Major | Medium | Open |  |  | TC_060
BUG-008 | Merchant Signup / Shopper Signup / Add Address | Phone Number field does not enforce the starting-digit rule (must start with 9/8/7/6) on Merchant Signup, Shopper Signup, and Add Address forms | 1. On Merchant Signup (User Information step) or Shopper Signup, enter a 10-digit phone number starting with 5 2. Proceed | Validation error should be shown; number starting with a digit other than 9/8/7/6 should be rejected | No validation error shown; the form proceeds with an invalid phone number | Major | Medium | Open |  |  | TC_067, TC_098, TC_160
BUG-009 | Merchant Signup | Commission field on Company Information step accepts values below the documented minimum of 20% | 1. On Merchant Signup, Company Information step, enter Commission = 10% 2. Click Next | Validation error should be shown; minimum 20% should be enforced | No validation error shown; value below 20% is accepted | Major | Medium | Open |  |  | TC_078
BUG-010 | Search Product | Search results page briefly flashes a false 'Sorry No Data Found' state before correctly displaying matching results | 1. On landing page, click the Search Bar 2. Type a valid, existing product name 3. Click the Search icon 4. Observe the screen immediately after clicking | A loading indicator should be shown, followed directly by the correct list of matching results, with no false-negative message | A brief loading state is followed by a flash (~0.5 seconds) of a large 'Sorry No Data Found' message and image, before the correct results are rendered | Minor | Low | Open |  |  | TC_114
BUG-011 | Search Product | Submitting an empty search query navigates to an irrelevant page instead of the full catalog or a prompt | 1. Click the Search Bar 2. Leave it blank 3. Click the Search icon | Either the full product catalog or a prompt to enter a search term should be shown | Page loads a screen that resembles the home page but is not correct/relevant in context | Minor | Low | Open |  |  | TC_117
BUG-012 | Search Product | Search results differ depending on the case of the query (search is not case-insensitive) | 1. Search a product name in all uppercase (e.g. 'SHOES') 2. Repeat the same search in all lowercase ('shoes') 3. Compare results | Both searches should return the same matching results | Uppercase and lowercase versions of the same search term return different results | Major | Medium | Open |  |  | TC_119
BUG-013 | Add to Cart | Clicking the minus (-) button on a cart item with quantity 1 does not remove the item or decrement the cart count | 1. Add a product to cart (quantity 1) 2. Open Cart 3. Click the minus (-) button on that item | Item quantity should decrement to 0 and the product should be removed from the cart; cart count should update accordingly | Product remains in the cart with no change; cart count does not decrement | Major | Medium | Open |  |  | TC_136
BUG-014 | Add Address | Address is saved with no delivery-availability warning when the entered pincode is not on the serviceable list | 1. On Add Address form, enter all valid mandatory fields 2. Enter a pincode NOT on the serviceable list (e.g. 110001) 3. Click 'Add Address' | Address should be rejected, or clearly flagged as non-deliverable, before being saved | Address is saved successfully with no indication that the pincode is non-serviceable | Major | High | Open |  |  | TC_159

## Execution Summary
ShoppersStack — Test Execution Summary
Module | Total TCs | Pass | Fail | Blocked | Not Executed | % Executed
Admin Signup | 51 | 47 | 4 | 0 | 0 | 100%
Admin Login | 9 | 7 | 2 | 0 | 0 | 100%
Merchant Signup | 27 | 24 | 3 | 0 | 0 | 100%
Merchant Login | 5 | 3 | 1 | 1 | 0 | 100%
Shopper Signup | 13 | 11 | 2 | 0 | 0 | 100%
Shopper Login | 8 | 8 | 0 | 0 | 0 | 100%
Search Product | 14 | 11 | 3 | 0 | 0 | 100%
Add to Cart | 14 | 13 | 1 | 0 | 0 | 100%
Buy Product | 7 | 7 | 0 | 0 | 0 | 100%
Add Address | 16 | 14 | 2 | 0 | 0 | 100%
Place Order | 19 | 19 | 0 | 0 | 0 | 100%
TOTAL | 183 | 164 | 18 | 1 | 0 | 99.45%
Legend: Pass = feature works as expected ¦ Fail = defect found (see Defect Log) ¦ Blocked = cannot be tested due to a dependency defect ¦ Not Executed = pending manual execution