## RTM
ShoppersStack — Requirement Traceability Matrix (RTM)
Maps every Product Backlog item to its Test Scenarios, Test Cases, execution results, and linked defects
Backlog ID | User Story | Priority | Story Points | Test Scenario IDs | Test Case ID Range | Total TCs | Pass | Fail | Blocked | Defects Linked | Coverage Status
| As a customer, I want to open Shoppersstack website. | High | 1 | TS_01 | TC_01 | 1 | 1 | 0 | 0 | None | Fully Tested — No Defects
PB-01 | As an admin, I want to create an Admin account so that I can manage the ShoppersStack platform. | High | 5 | TS_02-TS_15 | TC_02, TC_03, TC_08-TC_58 | 53 | 49 | 4 | 0 | BUG-002, BUG-003, BUG-004 | Fully Tested
PB-04 | As an admin, I want to log in securely so that I can access the Admin home page. | High | 2 | TS_16-TS_17 | TC_059-TC_067 | 9 | 7 | 2 | 0 | BUG-006, BUG-007 | Fully Tested
PB-02 | As a business owner, I want to sign up as a Merchant so that I can list and sell products. | High | 5 | TS_03,TS_18-TS_22 | TC_04-TC_05, TC_068-TC_094 | 29 | 26 | 3 | 0 | BUG-001, BUG-008, BUG-009 | Fully Tested (Blocker found)
PB-05 | As a Merchant, I want to log in and add/edit products so that I can manage my catalog. | High | 2 | TS_23-TS_24 | TC_95-TC_99 | 5 | 3 | 1 | 1 | BUG-001, BUG-006 | Partially Blocked (dependent on BUG-001)
PB-03 | As a customer, I want to sign up as a Shopper so that I can browse and purchase products. | High | 5 | TS_04, TS_25-TS_27 | TC_06, TC_07, TC_100-TC_112 | 15 | 13 | 2 | 0 | BUG-005, BUG-008 | Fully Tested
PB-06 | As a Shopper, I want to log in securely so that I can access the shopping platform. | High | 3 | TS_28-TS_29 | TC_113-TC_120 | 8 | 8 | 0 | 0 | None | Fully Tested — No Defects
PB-07 | As a Shopper, I want to search for a specific product or browse by category. | Medium | 5 | TS_30, TS_32-TS_35 | TC_121, TC_123-TC_136 | 15 | 12 | 3 | 0 | BUG-010, BUG-011, BUG-012 | Fully Tested
PB-08 | As a Shopper, I want to add products to my cart from search results or landing page. | High | 5 | TS_31, TS_36-TS_38 | TC_122, TC_137-TC_150 | 15 | 14 | 1 | 0 | BUG-013 | Fully Tested
PB-09 | As a Shopper, I want to buy a product directly or from my cart. | High | 5 | TS_39-TS_41 | TC_151-TC_157 | 7 | 7 | 0 | 0 | None | Fully Tested — No Defects
PB-10 | As a Shopper, I want to add a delivery address with pincode serviceability. | Medium | 3 | TS_36-TS_41 | TC_149-TC_164 | 17 | 15 | 2 | 0 | BUG-008, BUG-014 | Fully Tested
PB-11 | As a Shopper, I want to place an order using COD, Net Banking, Debit Card or Credit Card. | High | 8 | TS_49-TS_54 | TC_175-TC_193 | 19 | 19 | 0 | 0 | None | Fully Tested — No Defects
PB-12 | As a Shopper, I want to generate and view vouchers/coupons so that I can save on future purchases. | Medium | 7 | TS_56, TS_58-TS_64 | TC_195, TC_197-TC_216 | 21 | 14 | 7 | 0 | BUG-015, BUG-016, BUG-017, BUG-019, BUG-020 | Fully Tested (Critical found)
PB-13 | As a Shopper, I want to redeem a voucher at checkout so that the order cost is reduced. | Medium | 3 | TS_52-TS_53 | TC_204-TC_219 | 18 | 16 | 2 | 0 | BUG-015, BUG-018 | Fully Tested
TOTAL |  |  | 59 |  |  | 232 | 204 | 27 | 1
Product Backlog items fully mapped to test scenarios and test cases. 100% requirement traceability achieved — every user story has at least one executed test case.